## Slide 1: Learning Management System transfer plan
Presented by: Shazia Hoodbhoy
Bridge to PGVLE
Notes: Standard title slide

## Slide 2
October-November 2024
Confirmation of National TEL support for project
Soft launch - PGVLE & EoE BL presentation to HoS, DMEs, APDs
BL Governance and user meetings – BL leads to develop plan to review Bridge and Panopto content for own school/specialty
Contract extensions with current providers
Request additional resource from national TEL team
PGVLE and EoE BL teams – technical aspects (file format, architecture of EoE PGVLE space, live session booking process)
November 2024 –January 2025
Communication to admin/ educators/ trainees
Content review and curation with QA
Identify Early adopter Schools
Pilot shadow transfer of content – tech issue identification
Develop training plan for administrators, educators, learners
Governance structure
SOPs, User guides
Feb - March 2025
Review archived content
Identify Second wave Schools
April 2025
Commence final year of Bridge contract
Workshops and presentations at Spring symposium
Early Adopters start using PGVLE platform (shadow then live)
Develop plan for transfer of all Schools and specialties
May 2025 -
Transfer of schools and specialties- iterative
July 2025
Onboarding of new learners to PGVLE
November 2025
Complete transfer of all schools and specialties
Establish BAU with appropriate administrator support
Timeline for transition to PGVLE
Notes: Plain slide with subhead and bullets

## Slide 3: What’s happening Jan-March
Extension of contracts to ensure continuing delivery of education throughout the transition period
EoE BL team continuing to meet with BL leads from all areas to talk about the transfer to the PGVLE and what this will mean for them – this includes non-medical users
Working with the national TEL team to work through technical aspects of transfer
Working with PGVLE team to set up the skeleton for EoE on the PGVLE platform
Confirming first wave Schools to upload content to PGVLE
Identifying key educators from all Schools to have access to PGVLE
Recording training videos for PGVLE migration
Working with PGVLE to look at options for fellowships next year
Working with PGVLE to develop wider Governance structure

## Slide 4: What’s next and what you need to do
Please do not build any more of your learning material in Bridge. We will still be using Bridge for the next year, but material built in powerpoint or saved as SCORM files will be more straightforward to transfer to the new platform
Complete your current Bridge content “spring clean” and review of archived content
Continue to use the template for reviewing content (available from the EoE BL team)
BL leads across the region
  Please ensure the transition is a standing item on the agenda for your School Board or specialty education meetings.
  Please get in touch with the EoE BL team now to start planning your transition in more detail.
  If you have enthusiastic educators/authors who could start to explore the PGVLE please send their details to the EoE BL team
  Please ensure your team is represented at the governance and user group meetings - these meetings will be essential in progressing the transition.
  Next meeting is tomorrow 27/2 at 10am – everyone is welcome!

## Slide 5: Contact details
Please do talk to your Blended Learning Lead, and contact the EoE BL team if you have any questions:
EoE Central Blended Learning team : england.blendedlearning.eoe@nhs.net
EoE Associate Postgraduate Dean for Blended Learning : s.hoodbhoy@nhs.net
EoE Senior Fellow for Blended Learning: sohel.samad2@nhs.net
Webpage for transition: https://heeoe.hee.nhs.uk/blended-learning-platform/pgvle-migration
Link to PGVLE demo video: https://youtu.be/8Btduf7IknY?si=TsVgGGqf-3IRbYck
Please do get in touch if you have any questions and check the website for links to extra resources.