**Stakeholder Report Form  
EoE Primary Care School Board Meeting**

| Programme / Workstream Name: | Transition Project and Post CCT IMG Support Fellows | | |
| --- | --- | --- | --- |
| Programme Lead: | Dr Sunil Gupta | | |
| PCS School Strategy Objective: | Learner Support | | |
| Period of Update: | From 4th February 2025 until 24th June 2025 | RAG Status for project: | Green |
| Programme / Workstream Summary | | | |
| The Consulting and Thinking days have restarted and are working well.  Successful Area TPD Development Day on 19th June 2025  Report produced by the last set of Post CCT IMG Support Fellows highlighted the significant difference they made (see attached report). | | | |
| Key Highlights | | | |
| See above. | | | |
| Decisions made since last update | | | |
| Because of resource constraints, the next cohort of IMG Support Fellows will be pre CCT and will be for only 8 months. They will be paid for working in this role for 2 sessions a week. They are likely to be less effective in this role than the Post CCT IMG Support Fellows who had already passed the MRCGP exam and were highfliers who were very pro-active and skilled. | | | |
| KPIs | | Financial Performance | |
|  | |  | |
| Operational Updates | | Progress on previous goals | |
|  | |  | |
| Risk Assessment Overview: *(Issues, Risks, Concerns, Barriers etc)* | | Governance and Compliance | |
|  | |  | |
| Stakeholder engagement | | | |
|  | | | |
| Future Outlook (Upcoming priorities, initiatives, or areas of focus) | | | |
|  | | | |
| Conclusion | | | |
| There continues to be good work in supporting International Medical Graduate GP Trainees address the issues of differential attainment. | | | |