**Stakeholder Report Form
EoE Primary Care School Board Meeting**

| Programme / Workstream Name: | Assessment |
| --- | --- |
| Programme Lead: | Jon Rouse |
| PCS School Strategy Objective: | Quality Assurance |
| Period of Update: | Feb to July 25 | RAG Status for project: | Green |
| Programme / Workstream Summary |
| Strategic oversight of assessment processes and policies for GP trainees |
| Key Highlights |
| Developed new policies for managing TOOT.Supported new administrators in their role assisting GP assessment. Delivered various assessment updates at educator days |
| Decisions made since last update  |
| Work ongoing with Will Bentley to develop a new ARCP checklist. |
| KPIs | Financial Performance |
| Ensuring consistency in ARCP panels.Keeping outcome 5 rates low. | NA |
| Operational Updates | Progress on previous goals |
| Megan and Tanaka now helping with GP ARCPs. Team remains under pressure due to restructuring of NHSE.  | Updated guidance for panels on managing TOOT – COMPLETEContinue to provide regular panel chair training and assessment updates at educator/TPD development days - Ongoing |
| Risk Assessment Overview: *(Issues, Risks, Concerns, Barriers etc)* | Governance and Compliance |
| Limited capacity of assessment team but managing well at present.  | Quality visit from the RCGP few developmental outcomes. Results of RCGP quality assurance presented to ADs and TPDs.  |
| Stakeholder engagement |
| Lay reps invited to attend all central ARCP panels |
| Future Outlook (Upcoming priorities, initiatives, or areas of focus) |
| Continue to provide regular panel chair training and assessment updates at educator/TPD development days.GP Assessment lead to continue to attend national DARG meetings to discuss ARCP processes and policies. Start to look at how AI may streamline ARCP processes. |
| Conclusion |
| Currently progressing well with external uncertainty of restructuring of NHSE. |